## TEI
TEI Implementation Progress Reporting
Key
Grey = past activities completed
Green =ongoing and future activities not completed
*start and end points indicated by dark shading
|  | 2017 | 2018 | [11 empty] | 2019 | [11 empty] | 2020
| Category | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan
Cyclical Ongoing Tasks
Monthly Status Report of Progress toward Grant Deliverables in the form of a Gannt Chart | Admin
Quarterly Report of Financials and Progress at TEI Governing Board Meetings | Fiscal
Annual Report of Financials and Progress toward Grant Deliverables. | Fiscal
TEI Governing Board Appointments | Admin
TEI Governing Board Meetings Dates to be confirmed | Admin
Upcoming / Ad-Hoc
Daniels Fund Meeting (Fall, 2019) | Admin
E4 Implementation Plan with Entagled Solutions | Admin
August 24 site visit Laramie | Admin
Identify and Address TEI Staffing Needs | Admin
Managing Director
Hiring for E4 Director
Hiring for Marketing Director | Admin
Identify New Office Space for TEI | Admin
Change in scope of service on Marzano Research Contract or cancellation of current contract | Admin
Develop a longterm TEI sustaining budget for fund development purposes | Fiscal
Promo Video for TEI - Michael involved in Promo Video | Marketing & Outreach
WYECON Support for conference
Support Educators Rising - Under Review for Cost Considerations | Admin
Create WY Educators Rising Chapter - Three Pilot Sites, Fremont, Converse and Laramie County | Admin
Marketing & Outreach to School Districts for Educators Rising Signup - On Hold During Pilots | Marketing & Outreach
Coordinate sub-grants / MOU for School Districts - On Hold During Pilots | Admin
Set Dates and Location for 2019 Educators Rising Wyoming Conference and Competition - On Hold During Pilots and Negotiations with Ed Rising National | Admin
Create website for WYCOLA | Marketing & Outreach
Special Projects Proposal to UW Trustees Reserve Account for TEI Core Program Investment
Trademark and Register UW-E4 Graphic and Logo and TEI Logo
TEI Governing Board SubCommittee on Finance and Fund Raising - White Paper
Launch TEI Implementation Team
Ongoing
Connect TEI with UW Leaders and other Initaitives | Strategic Partnerships
Work with Project Lead the Way | Strategic Partnerships
Schedule meeting with Rick Hess from American Enterprise Institute | Strategic Partnerships
Request support from Education Advisory Board, specifically through Brian Schueler. | Strategic Partnerships
Create Identity for TEI Innovations | Marketing & Outreach
Promote TEI via Mass Media | Marketing & Outreach
TEI Website Updates and Maintenance | Marketing & Outreach
Social Media Presence: Facebook, etc. | Marketing & Outreach
TEI Outreach in Wyoming | Marketing & Outreach
Completed
Update TEI Strategic Plan to describe the hand-off of innovation responsibility from TEI to the College of Education | Strategic Partnerships | x
Legislative Luncheon - Planning for Feb 2019 | Strategic Partnerships
Seek a Consultant to Advise on the Implementation of UW•E4 | Admin
America Succeeds / Wyoming Excels _ Met with Clayton in Jan 2019 | Strategic Partnerships
Order materials and supplies for 2019 Pilots and Implementation | Admin
ONGOING TASKS

## E4
E4 Implementation Progress Reporting
Key
Dark shading = significant activities, and beginning/end of milestone
Light shading = activity duration
[6 empty] | Year 1 | [11 empty] | Year 2 | [11 empty] | Year 3
| Type | Fall 2018 |  |  |  | Spring 2019 |  |  |  |  | Summer 2019 |  |  | Fall 2019 |  |  |  | Spring 2020 |  |  |  |  | Summer 2020 |  |  | Fall 2020 |  |  |  | Spring 2021 |  |  |  |  | Summer 2021 |  |  | Fall 2021
Exploration (E1) |  | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Launch Educators Rising pilot with 1-3 districts | activity | bar: Fall 2018 Sep to Fall 2018 Nov
Launch Exploration Pilot Design Team | milestone | bar: Spring 2019 Jan to Spring 2019 May
Pilot Early Explorer onramp | significant activity | bar: Spring 2019 Jan to Spring 2020 Jan
Launch early explorer onramp | milestone | bar: Summer 2019 Aug
Build measurement system to evaluate onramps and student quality | activity | bar: Summer 2019 Jun to Spring 2020 Jan
Identify a technology tool (CRM) to track student exploration engagement | activity | bar: Summer 2019 Jun to Spring 2020 Jan
Build Career Seeker onramp | significant activity | bar: Spring 2019 Jan to Spring 2020 Jan
Develop approaches for other onramps e.g., place-based learners, community college students | activity | bar: Spring 2019 Jan to Fall 2019 Dec
Begin building relationships with community colleges | activity | bar: Spring 2019 Jan to Fall 2019 Dec
Develop marketing materials and student info for Career Seekers | activity | bar: Summer 2019 Jun to Fall 2019 Dec
Sign 5 MOUs with districts | milestone | bar: Fall 2019 Sep
Pilot Career Seeker onramp | bar: Spring 2020 Jan to Fall 2020 Dec
Launch Career Seeker onramp pilot | milestone | bar: Spring 2020 Jan
Continue to expand onramp access with out reach to districts and community colleges | activity | bar: Spring 2020 Jan to Fall 2020 Dec
Develop marketing materials to illustrate student options and participation pathways | activity | bar: Spring 2020 Jan to Fall 2020 Dec
Develop classroom visit / shadowing opportunities | activity | bar: Spring 2020 Jan to Fall 2020 Dec
Design first state conference | activity | bar: Fall 2020 Sep to Fall 2020 Dec
Track progress of all onramps | significant activity | bar: Spring 2020 Jan to Fall 2020 Dec
Gather baseline for satisfaction of program from students, schools, and districts | milestone | bar: Spring 2020 Jan
Determine UW admission and selection criteria | activity | bar: Spring 2020 Jan to Fall 2020 Dec
Conduct Career Seeker survey | activity | bar: Spring 2020 Jan to Fall 2020 Dec
Determine scalability of EdRising or like exploration program | activity | bar: Spring 2019 May to Summer 2019 Aug; Fall 2020 Sep to Fall 2020 Dec
Determine whether to pilot and scale Exploration activities | milestone | bar: Fall 2019 Sep; Fall 2020 Sep to Fall 2020 Dec
Leverage momentum to expand pilots | significant activity | bar: Spring 2021 Jan to Fall 2021 Dec
Expand pilots for both onramps; goal of 20 students enrolling in UW from each | milestone | bar: Spring 2021 Jan
Host first state conference to increase awareness and educate | activity | bar: Spring 2021 Jan to Spring 2021 May
Develop communications plan to encourage participation and communicate results of engagement approaches | activity | bar: Spring 2021 Jan to Summer 2021 Aug
Determine and make changes to program experiences and student pathways while scaling | activity | bar: Spring 2021 Jan to Fall 2021 Dec
Determine investments in each onramp based on which produced higher satisfaction and higher quality graduates | milestone | bar: Fall 2021 Sep
Measure enrollment from onramps | activity | bar: Fall 2021 Sep to Fall 2021 Dec
Measure impact of engagement activities and onramps on student performance and retention | activity | bar: Fall 2021 Sep to Fall 2021 Dec
Experiential Learning (E2)
Launch Experiential Learning Pilot Design Team | milestone | bar: Fall 2018 Dec to Spring 2019 May
Determine approach to content development | milestone | bar: Fall 2018 Dec
Determine sequential approach to developing competency-based and online content | milestone
Build elementary and special education program content | significant activity | bar: Spring 2019 Jan to Fall 2019 Dec
Pilot online course development for elementary and special education in series of two-week working sessions | milestone | bar: Fall 2019 Sep to Fall 2019 Dec
Design program through iterative development approach; include stakeholder working sessions | activity | bar: Summer 2019 Jun to Fall 2019 Dec
Build awareness and enthusiasm among faculty and deans; identify champions to engage in program design | activity | bar: Spring 2019 Jan to Fall 2019 Dec
Develop methodology for testing and revising modules | activity | bar: Spring 2019 Jan to Fall 2019 Dec
Conduct user testing with students and alumni prior to launch | activity | bar: Fall 2019 Sep to Fall 2019 Dec
Develop approach to ongoing data capture and gather baseline performance data | activity | bar: Spring 2019 Jan to Fall 2019 Dec
Pilot elementary and special education programs | significant activity | bar: Spring 2020 Jan to Fall 2020 Dec
Launch initial pilot | milestone | bar: Spring 2020 Jan
Ensure accessibility of pilots remotely and in-person | activity | bar: Spring 2020 Jan to Fall 2020 Dec
Use stakeholder working sessions to inform content development approach to new pilots and revisions needed | activity | bar: Spring 2020 Jan to Fall 2020 Dec
Capture data on student performance in pilots | activity | bar: Spring 2020 Jan to Fall 2020 Dec
Build early childhood and secondary education programs | significant activity | bar: Spring 2020 Jan to Fall 2020 Dec
Use existing data to inform development of new pilots | activity | bar: Spring 2020 Jan to Summer 2020 Aug
Build secondary ed pilots considering additional content knowledge required | activity | bar: Spring 2020 Jan to Fall 2020 Dec
Pilot early childhood and secondary education programs | significant activity | bar: Spring 2021 Jan to Fall 2021 Dec
Launch second set of competency based course pilots and revise based on content and pedagogy needs | milestone | bar: Spring 2021 Jan to Fall 2021 Dec
Establish baseline satisfaction with course content | milestone | bar: Spring 2021 Jan
Track student performance data after baseline and given course revisions | activity | bar: Spring 2021 Jan to Fall 2021 Dec
Leverage momentum to expand pilots | significant activity | bar: Spring 2021 Jan to Fall 2021 Dec
Scale elementary and special education programs with feedback on program quality, rigor, and student success | activity | bar: Spring 2021 Jan to Fall 2021 Dec
First pilot cohort begins residency | milestone | bar: Fall 2021 Dec
Determine course content, level of preparation, and readiness based on employer feedback | milestone | bar: Fall 2021 Dec
Embedded Practice (E3)
Launch Embedded Practice Pilot Design Team | milestone | bar: Spring 2019 Jan to Spring 2019 May
Design and build residency program | significant activity | bar: Spring 2019 Jan to Fall 2019 Dec
Recruit districts across WY | activity | bar: Spring 2019 Jan to Fall 2019 Dec
Recruit mentor teachers to participate | activity | bar: Spring 2019 Jan to Fall 2019 Dec
Design co-teaching residency model | activity | bar: Spring 2019 Jan to Fall 2019 Dec
Design professional development training for mentors | activity | bar: Spring 2019 Jan to Fall 2019 Dec
Design matching process between candidates and mentors | activity | bar: Spring 2019 Jan to Fall 2019 Dec
Annual Fall residency luncheon | milestone | bar: Fall 2019 Oct to Fall 2019 Nov; Fall 2020 Oct to Fall 2020 Nov; Fall 2021 Oct to Fall 2021 Nov
Determine the need for a facilitator to support student-mentor matching | activity | bar: Fall 2019 Sep to Fall 2019 Dec
Build infrastructure/measurement approach to support matching process and evaluation | activity | bar: Fall 2019 Sep to Fall 2019 Dec
Build infrastructure to track district engagement | activity | bar: Fall 2019 Sep to Fall 2019 Dec
All mentor and student feedback surveys and support materials developed; baseline survey deployed | milestone | bar: Fall 2019 Oct to Fall 2019 Nov
Pilot residency program | bar: Spring 2020 Jan to Fall 2020 Dec
Launch pilot residency program with districts and students, based on Design Team figures | milestone | bar: Spring 2020 Jan
Pilot program and determine objectives for scaling | activity | bar: Spring 2020 Jan to Fall 2020 Dec
Regularly consult with participating districts for continual feedback | activity | bar: Spring 2020 Jan to Fall 2020 Dec
Expand district outreach, communicating pilot progress | activity | bar: Spring 2020 Jan to Fall 2020 Dec
Monitor progress throughout residency | activity | bar: Spring 2020 Jan to Fall 2020 Dec
Develop tools to streamline mentor matching process and support relationship development | activity | bar: Spring 2020 Jan to Fall 2020 Dec
Track district involvement and interest in hosting students | activity | bar: Spring 2020 Jan to Fall 2020 Dec
Collect qualitative feedback to understand program strengths and weaknesses | activity | bar: Spring 2020 Jan to Fall 2020 Dec
Expand residency pilot to additional districts | significant activity | bar: Spring 2021 Jan to Fall 2021 Dec
Reach additional districts | milestone | bar: Spring 2021 Jan
First cohort transitions to full-time role; assess preparedness | activity | bar: Spring 2021 Jan to Summer 2021 Aug
Onboard new districts | activity | bar: Spring 2021 Jan to Summer 2021 Aug
Refine approach to matching, to create stronger matches and streamline processes | activity | bar: Spring 2021 Jan to Summer 2021 Aug
Determine objectives for scaling | activity | bar: Spring 2021 Jan to Summer 2021 Aug
Conduct Pilot Team working sessions with districts to determine how to strengthen program | activity | bar: Spring 2021 Jan to Fall 2021 Dec
Make revisions needed to achieve success at scale | activity | bar: Fall 2021 Sep to Fall 2021 Dec
Determine additional technology needs for scale | activity | bar: Fall 2021 Sep to Fall 2021 Dec
Entry into Profession (E4)
Design Entry into Profession | significant activity | bar: Spring 2019 Jan to Fall 2019 Dec
Launch Entry into Profession Pilot Design Team | milestone | bar: Spring 2019 Jan to Spring 2019 May
Determine programs and services that best serve newly inducted educators and their mentors | activity | bar: Spring 2019 Jan to Spring 2019 May
Determine best approaches and for incorporating Entry into Profession into COE teacher induction and mentor programs | activity | bar: Spring 2019 Jan to Spring 2019 May
Determine approaches for exposing pre-service educators and newly inducted educators to Entry into Profession programming | activity | bar: Spring 2019 Jan to Fall 2019 Dec
Pilot Entry into Profession program | significant activity | bar: Fall 2019 Sep to Spring 2020 May
Implement Entry into Profession in select COE programs and districts | milestone | bar: Fall 2019 Sep to Spring 2020 May
Partner in Deans for Impact Study, in order to strengthen/determine areas for program improvement | milestone | bar: Fall 2019 Sep to Fall 2021 Dec
Determine internal and external Entry into Profession personnel, infrastructure, and support needs | activity | bar: Summer 2020 Jun to Fall 2021 Dec
Collect and analyze Entry into Profession data | bar: Summer 2020 Jun to Summer 2020 Aug; Fall 2021 Nov to Fall 2021 Dec
Continuous program evaluation and improvement based on established metrics and evaluation | activity | bar: Summer 2020 Jun to Summer 2020 Aug; Fall 2021 Nov to Fall 2021 Dec

## TEI Innovations
E4 Implementation Progress Reporting
Key
Dark shading = significant activities, and beginning/end of milestone
Light shading = activity duration
[6 empty] | Year 1 | [11 empty] | Year 2 | [11 empty] | Year 3
| Type | Fall 2018 |  |  |  | Spring 2019 |  |  |  |  | Summer 2019 |  |  | Fall 2019 |  |  |  | Spring 2020 |  |  |  |  | Summer 2020 |  |  | Fall 2020 |  |  |  | Spring 2021 |  |  |  |  | Summer 2021 |  |  | Fall 2021
Common Indicator System |  | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Design Common Indicator System | significant activity | bar: Spring 2019 Jan to Fall 2019 Dec
Launch Common Indicator System (CIS) Pilot Design Team | milestone | bar: Spring 2019 Jan to Spring 2019 May
Determine best approaches for incorporating Common Indicator System into COE programs and E4 model | activity | bar: Spring 2019 Jan to Fall 2019 Dec
Determine approaches and mechanisms for engaging students with CIS results | bar: Spring 2019 Jan to Fall 2019 Dec
Create timelines and approaches for COE program effectiveness, based on CIS results | bar: Spring 2019 Jan to Fall 2019 Dec
Pilot CIS program | significant activity | bar: Fall 2019 Sep to Spring 2020 May
Implement CIS into select programs of study and districts | milestone | bar: Fall 2019 Sep to Spring 2020 May
Partner in Deans for Impact Study, in order to strengthen/determine areas for program improvement | milestone | bar: Fall 2019 Sep to Fall 2021 Dec
Determine internal and external CIS personnel, infrastructure, and support needs | activity | bar: Summer 2020 Jun to Fall 2021 Dec
Collect and analyze CIS data | bar: Summer 2020 Jun to Summer 2020 Aug; Fall 2021 Nov to Fall 2021 Dec
Continuous program evaluation and improvement based on results of CIS collected data and other forms of feedback and analysis from Deans for Impact | activity | bar: Summer 2020 Jun to Summer 2020 Aug; Fall 2021 Nov to Fall 2021 Dec
Ethical Educator
Design Ethical Educator program | significant activity | bar: Fall 2018 Sep to Fall 2019 Dec
Launch Ethical Educator Pilot Design Team | milestone | bar: Spring 2019 Jan to Spring 2019 May
Determine approach to content development | milestone | bar: Spring 2019 Jan to Spring 2019 May
Determine courses most suitable for incorporating Ethical Educator | bar: Spring 2019 Jan to Spring 2019 May
Determine best approaches and timing for incorporating Ethical Educator into courses and into E4 Model | milestone | bar: Spring 2019 Jan to Spring 2019 May
Deploy Ethical Educator assessment | activity | bar: Spring 2019 Jan to Fall 2019 Dec
Pilot Ethical Educator program | significant activity | bar: Fall 2019 Sep to Spring 2020 May
Implement Ethical Educator pilot with select programs of study | milestone | bar: Fall 2019 Sep to Spring 2020 May
Determine internal and external Ethical Educator personnel, infrastructure, and support needs | activity | bar: Summer 2020 Jun to Summer 2020 Aug
Continuous evaluation and improvement of Ethical Educator, based on results of collected data and other forms of feedback and analysis | activity | bar: Summer 2020 Jun to Summer 2020 Aug
Assess and Continue Ethical Educator | significant activity | bar: Spring 2021 Jan to Fall 2021 Dec
Continue and/or expand Ethical Educator, based on data and feedback | activity | bar: Spring 2021 Jan to Fall 2021 Dec
Mursion Augmented Reality
Pilot Mursion program | significant activity | bar: Fall 2018 Sep to Fall 2019 Dec
Continue/Expand Mursion pilot program with COE teacher education program (launched in 2017 with Foundations courses), to include methods courses, select secondary math, science and agriculture sections, and graduate-level counseling sections | milestone | bar: Fall 2018 Sep; Fall 2018 Dec
Monitor pilot program results, tracking needs and scaling capacity | activity | bar: Fall 2018 Sep to Fall 2019 Dec
Collect qualitative and quantitative data to guide needs and scaling | activity | bar: Fall 2018 Sep to Fall 2019 Dec
Design and Implement Mursion | significant activity | bar: Fall 2018 Sep to Fall 2019 Dec
Launch Mursion Design Team | milestone | bar: Spring 2019 Jan to Spring 2019 May
Plan Mursion expansion to include other COE departments | activity | bar: Fall 2018 Sep to Fall 2019 Dec
Demonstrate and promote Mursion through local, state, and regional conferences, trainings, and district meetings | activity | bar: Fall 2018 Sep to Fall 2019 Dec
Recruit districts across WY, through demonstrations and promotions | activity | bar: Spring 2019 Jan to Fall 2019 Dec
Determine best approaches for incorporating Mursion into COE programs and E4 model | activity | bar: Spring 2019 Jan to Fall 2019 Dec
Determine/Project internal and external Mursion personnel, infrastructure, and support needs, with scaling in mind | activity | bar: Spring 2019 Jan to Fall 2020 Dec
Continuous evaluation and improvement of Mursion, based on results of collected data and other forms of feedback and analysis | activity | bar: Spring 2019 Jan to Fall 2019 Dec
Expand Mursion | significant activity | bar: Spring 2021 Jan to Fall 2021 Dec
Continue expansion to include additional COE programs, WY districts, and areas of E4 beyond teacher education programs | activity | bar: Spring 2021 Jan to Fall 2021 Dec
Determine/Project internal and external Mursion personnel, infrastructure, and professional development/training needs, with scaling in mind | activity | bar: Spring 2021 Jan to Fall 2021 Dec
Continuous evaluation and improvement based on results of collected data and other forms of feedback and analysis | activity | bar: Spring 2021 Jan to Fall 2021 Dec
Wyoming Coaching Laboratory- WYCOLA
Complete WYCOLA Pilot (Launched Spring 2018) | milestone | bar: Fall 2018 Sep to Spring 2019 May
Launch WYCOLA Design Team | milestone | bar: Spring 2019 Jan to Spring 2019 May
Pilot WYCOLA 2.0 and build additional induction/ professional development programs | significant activity | bar: Spring 2019 Jan to Fall 2019 Dec
Determine best approaches for incorporating WYCOLA into COE programs and E4 model | activity | bar: Spring 2019 Jan to Fall 2019 Dec
Build plan to transition new teacher support from UW to districts | activity | bar: Spring 2019 Jan to Fall 2019 Dec
Develop strong student-teaching mentor and teacher induction mentor programs | activity | bar: Spring 2019 Jan to Fall 2019 Dec
Conduct working sessions with districts, and develop feedback mechanisms to learn how best to collaborate | activity | bar: Fall 2019 Sep to Fall 2019 Dec
Monitor progress of WYCOLA integration into COE programs and E4 model | activity | bar: Fall 2019 Sep to Fall 2019 Dec
Assess WYCOLA Mentor Support Effectiveness | significant activity | bar: Spring 2021 Jan to Fall 2021 Dec
Continue to expand district network and mentor support | activity | bar: Spring 2021 Jan to Fall 2021 Dec
Form an engaged corhort of UW alumni as WYCOLA-trained mentors | activity | bar: Spring 2021 Jan to Fall 2021 Dec
Reassess technology and infrastructure needs as program scales | activity | bar: Spring 2021 Jan to Fall 2021 Dec
Wyoming Early Childhood Outreach Network- WYECON
Design WYECON program | significant activity | bar: Spring 2019 Jan to Fall 2019 Dec
Launch WYECON Pilot Design Team | milestone | bar: Spring 2019 Jan to Spring 2019 May
Collaborate with UW Early Childhood (EC) program in developing bachelor's degree program | activity | bar: Spring 2019 Jan to Spring 2019 May
Determine EC courses most suitable for distance and brick-and-mortar delivery | activity | bar: Spring 2019 Jan to Summer 2019 Aug
Identify and create relevant and accessible EC professional development | bar: Spring 2019 Jan to Summer 2019 Aug
Determine best approaches and timing for incorporating WYECON into E2 and E3 of the E4 Model | milestone | bar: Spring 2019 Jan to Spring 2019 May
Determine internal and external WYECON personnel, infrastructure, and support needs | activity | bar: Spring 2019 Jan to Summer 2019 Aug
Establish metrics for WYECON assessment and continuous improvement | activity | bar: Spring 2019 Jan to Spring 2019 May
Pilot WYECON program | significant activity | bar: Fall 2019 Sep to Fall 2020 Dec
Implement WYECON pilot in UW COE, select districts, select community colleges, and select communities | milestone | bar: Fall 2019 Sep to Fall 2020 Dec
Re-evaluate internal and external WYECON personnel, infrastructure, and support needs | activity | bar: Summer 2020 Jun to Summer 2020 Aug
Assess and Expand WYECON program | significant activity | bar: Spring 2021 Jan to Fall 2021 Dec
Continue and/or expand WYECON program, including establishment of additional partner districts, employers, community entities, and community colleges, based on established metrics | milestone | bar: Spring 2021 Jan to Fall 2021 Dec
Review EC program, curriculum, and student results | activity | bar: Fall 2021 Oct to Fall 2021 Dec