## Task List
CPM Project Management Example1
ABM Design Project - Task List
Activity | Description
A | Negotiate contract
B | Preliminary missile design
C | Design guidance system
D | Select missile configuration
E | Design missile frame
F | Design missile fuel system
G | Design rocket engine
H | Final missile design
I | Fabricate missile frame, fuel system and engine
J | Fabricate guidance system
K | Test missile frame, fuel system and engine
L | Test guidance system
M | Assemble completed missile
1Ragsdale, Cliff T., Spreadsheet Modeling and Decision Analysis, A Practical Introduction to Management Science, Course Technology, Inc., Cambridge, MA, 1995

## Relationship Diagram
CPM Project Management Example
ABM Design Project - Basic Relationship Diagram
C
H
F
G
D
B
A
J
K
L
M
I
E

## Time Table-Forward Pass
CPM Project Management Example
ABM Design Project - Time Table, Forward Pass
Activity | Description | Time | EST | EFT
|  | (days) |  |  | Cell Formulas
A | Negotiate contract | 3 | 0 | 3 | 0 | =D7+C7
B | Preliminary missile design | 45 | 3 | 48 | =+E7 | =D8+C8
C | Design guidance system | 62 | 48 | 110 | =+E8 | =D9+C9
D | Select missile configuration | 12 | 48 | 60 | =+E8 | =D10+C10
E | Design missile frame | 71 | 60 | 131 | =+E10 | =D11+C11
F | Design missile fuel system | 123 | 60 | 183 | =+E10 | =D12+C12
G | Design rocket engine | 97 | 60 | 157 | =+E10 | =D13+C13
H | Final missile design | 59 | 183 | 242 | =MAX(E9,E11:E13) | =D14+C14
I | Fabricate missile frame, fuel system and engine | 159 | 242 | 401 | =+E14 | =D15+C15
J | Fabricate guidance system | 95 | 242 | 337 | =+E14 | =D16+C16
K | Test missile frame, fuel system and engine | 31 | 401 | 432 | =+E15 | =D17+C17
L | Test guidance system | 44 | 337 | 381 | =+E16 | =D18+C18
M | Assemble completed missile | 65 | 432 | 497 | =MAX(E17:E18) | =D19+C19
Key Points: The forward pass
-- The earliest start time (EST) for the initial activity in a project is time zero.
* The earliest start time of an activity is equal to the latest (or maximum) earliest finish time (EFT) of the activities directly preceding it.
* The earliest finish time of an activity is equal to its earliest start time plus the time required to perform the activity.

## Time Table Backward Pass
CPM Project Management Example
ABM Design Project - Time Table, Backward Pass
Activity | Description | Time | EST | EFT | LST | LFT | Cell Formulas
|  | (days) |  |  |  |  | LST | LFT
A | Negotiate contract | 3 | 0 | 3 | 0 | 3 | =G7-C7 | =F8
B | Preliminary missile design | 45 | 3 | 48 | 3 | 48 | =G8-C8 | =MIN(F9:F10)
C | Design guidance system | 62 | 48 | 110 | 121 | 183 | =G9-C9 | =F14
D | Select missile configuration | 12 | 48 | 60 | 48 | 60 | =G10-C10 | =MIN(F11:F13)
E | Design missile frame | 71 | 60 | 131 | 112 | 183 | =G11-C11 | =F14
F | Design missile fuel system | 123 | 60 | 183 | 60 | 183 | =G12-C12 | =F14
G | Design rocket engine | 97 | 60 | 157 | 86 | 183 | =G13-C13 | =F14
H | Final missile design | 59 | 183 | 242 | 183 | 242 | =G14-C14 | =MIN(F15:F16)
I | Fabricate missile frame, fuel system and engine | 159 | 242 | 401 | 242 | 401 | =G15-C15 | =F17
J | Fabricate guidance system | 95 | 242 | 337 | 293 | 388 | =G16-C16 | =F18
K | Test missile frame, fuel system and engine | 31 | 401 | 432 | 401 | 432 | =G17-C17 | =F19
L | Test guidance system | 44 | 337 | 381 | 388 | 432 | =G18-C18 | =F19
M | Assemble completed missile | 65 | 432 | 497 | 432 | 497 | =G19-C19 | =E19
Key Points: The backward pass
* The latest finish time (LFT) for the final activity in a project is equal to its earliest finish time as determined by the forward pass.
* The latest finish time for any other activity is equal to the earliest (or minimum) latest finish time of the activities directly following (or succeeding) it.
* The latest start time of an activity is equal to its latest finish time minus the time required to perform the activity.

## Time Table Find Critical Path
CPM Project Management Example
ABM Design Project - Time Table, Determining Critical Path
Activity | Description | Time | EST | EFT | LST | LFT | Slack | Criticality
(days)
A | Negotiate contract | 3 | 0 | 3 | 0 | 3 | 0 | **
B | Preliminary missile design | 45 | 3 | 48 | 3 | 48 | 0 | **
C | Design guidance system | 62 | 48 | 110 | 121 | 183 | 73
D | Select missile configuration | 12 | 48 | 60 | 48 | 60 | 0 | **
E | Design missile frame | 71 | 60 | 131 | 112 | 183 | 52
F | Design missile fuel system | 123 | 60 | 183 | 60 | 183 | 0 | **
G | Design rocket engine | 97 | 60 | 157 | 86 | 183 | 26
H | Final missile design | 59 | 183 | 242 | 183 | 242 | 0 | **
I | Fabricate missile frame, fuel system and engine | 159 | 242 | 401 | 242 | 401 | 0 | **
J | Fabricate guidance system | 95 | 242 | 337 | 293 | 388 | 51
K | Test missile frame, fuel system and engine | 31 | 401 | 432 | 401 | 432 | 0 | **
L | Test guidance system | 44 | 337 | 381 | 388 | 432 | 51
M | Assemble completed missile | 65 | 432 | 497 | 432 | 497 | 0 | **
Key Points: Determining the Critical Path
* Critical activities have zero slack and cannot be delayed with delaying the completion of the project.
* Non-critical activities have some positive amount of slack that represents the amount of time by which the start times of these activities can be delayed with delaying the completion of the entire project, assuming that all predecessor activities start at their earliest start times.
Calculating Slack:
Slack for activity i = LSTi - ESTi

## Gantt Chart
CPM Project Management Example
ABM Design Project - Time Table, Determining Critical Path
Activity | Description | Time | EST | EFT | LST | LFT | Slack | Criticality
(days)
A | Negotiate contract | 3 | 0 | 3 | 0 | 3 | 0 | **
B | Preliminary missile design | 45 | 3 | 48 | 3 | 48 | 0 | **
C | Design guidance system | 62 | 48 | 110 | 121 | 183 | 73
D | Select missile configuration | 12 | 48 | 60 | 48 | 60 | 0 | **
E | Design missile frame | 71 | 60 | 131 | 112 | 183 | 52
F | Design missile fuel system | 123 | 60 | 183 | 60 | 183 | 0 | **
G | Design rocket engine | 97 | 60 | 157 | 86 | 183 | 26
H | Final missile design | 59 | 183 | 242 | 183 | 242 | 0 | **
I | Fabricate missile frame, fuel system and engine | 159 | 242 | 401 | 242 | 401 | 0 | **
J | Fabricate guidance system | 95 | 242 | 337 | 293 | 388 | 51
K | Test missile frame, fuel system and engine | 31 | 401 | 432 | 401 | 432 | 0 | **
L | Test guidance system | 44 | 337 | 381 | 388 | 432 | 51
M | Assemble completed missile | 65 | 432 | 497 | 432 | 497 | 0 | **
Creating Gantt Charts in Excel
This Gantt chart is a stacked horizontal bar chart that plots the EST and the time required to perform each activity. However, the bars for the EST for each activity are formatted so that they do not appear on the graph - giving the illusion that only the activity times are being graphed. To create a Gantt chart like this one:
1. Select the range covering the Description, Time and EST columns for all activities (shown in light green).
2. Click the Insert menu.
3. Click Chart.
Excels ChartWizard then prompts for a number of selections concerning the type of chart and how it should be formatted. Select the icons to display a stacked horizontal bar chart. When finished with the ChartWizard, the order of the bars needs to be reversed. To do this:
1. Right Click on the Activities axis and select the Format Axis menu.
2. Select the Scale tab.
3. Click the Categories in reverse order checkbox.
4. Make certain the Number of categories between tick-mark labels value is set to 1.
Finally, double click any of the bars representing the EST of any activity, select the Patterns option and select no borders and no area patterns. The basic Gantt chart is now complete. The chart can be further customized by clicking any element and specifying options in the resulting dialog boxes.